## Marketing Plan Data
Marketing Plan Data
Task | Status | Owner | Start Date | End Date | Estimated Cost | Actual Cost
Product Analysis | In Progress | John C. | 2017-02-28 |  | 1500 | 1250
Design Storyboards | In Progress | John C. | 2017-03-13 |  | 2000 | 1840
Review Storyboard Design | Complete | John C. | 2017-03-31 | 2017-04-15 | 1450 | 1450
Research Analysis Phase I | Delayed | Andrew L. |  |  | 3000
Advertising Content Creation Phase I | Delayed | Timothy S. |  |  | 500
Product Requirement Definitions | Delayed | Vivian A. |  |  | 575
Quality Control, Progress Reports | In Progress | Kamil A. | 2017-03-01 |  | 925 | 250
Create Storyboards | Not Started | John C. |  |  | 2000
Review Storyboards with Graphic Artists | Delayed | John C. |  |  | 1450
Research Analysis Phase II | Complete | Andrew L. | 2017-02-01 | 2012-02-28 | 3000 | 3200
Advertising Content Creation Phase II | Not Started | Timothy S. |  |  | 500
Note on H6: Mark M.: The cost is estimated to be increased by $500
Note on B10: Vivian A.: Requirements have been delayed due to customer changes
Note on B13: John C.: Task delayed as Design Storyboards task is not completed
Note on H14: Andrew L.: The cost was increased because of the additional research

## List Data (hidden)
Task Status
Not Started
In Progress
Complete
Delayed
Name | Title
John C. | Marketing Specialist
Mark M. | Marketing Manager
Kamil A. | Project Manager
Phil G. | Marketing Analyst
Andrew L. | Research Coordinator
Timothy S. | Marketing Specialist
Vivian A. | Marketing Analyst
Gabe F. | Associate Marketing Manager